## Table 1
Exhibit 9: Credit Fulfillment Checklist
Pierce County In Lieu Fee Program: Credit Fulfillment Checklist
Proposed Mitigation Project Details Impact(s) (Permit numbers, date) Proposed Receiving Site: Review process inception date
| Fulfillment Step | Responsible Party | Notes/Special conditions | Date completed | IRT Signoff
1 | Pierce County ILF Program selects preferred site | PCSWM |  |  | NA
2 | IRT review and approval of proposed receiving site and conceptual mitigation plan. | IRT | Legal for mitigation? Appropriate functional match provided by receiving site? __Potential for lift at proposed receiving site?
3 | Joint Public Notice on Site Selection and Conceptual Site Plan | COE/DOE | This public notice will also serve as the notice to amend the PCILF instrument by appending the site specific mitigation plan.
4 | Site Selection Approved | IRT
5 | Data collection/site assessments, including wetland delineation, rating and credit/debit assessment (delineation and wetland assessments may be limited to off-site delineation methods until site has been aquired). | PCSWM
6 | Submit and approve Spending Agreement | PCSWM/IRT | The spending agreement submittal may vary from this order and more than one spending agreement may be necessary for an ILF mitigation project depending on site specifics and baseline data needs.
7 | Develop draft mitigation plan, cost estimate, and credit generation proposal | PCSWM
8 | Submit draft site protection instrument | PCSWM
9 | Acquisition of site or easement | PCSWM
10 | Final draft mitigation plan completed | PCSWM | Including proposed credit release schedule
11 | Append Mitigation Plan to PCILF Instrument | COE/DOE
12 | Site Protection Instrument finalized and recorded | PCSWM
13 | IRT review and approval of Mitigation Plan and Credit Release Schedule | IRT | Proposed mitigation appropriate for original impacts(s)? No net loss requirements met?
14 | IRT Review and approval of site protection instrument | IRT
15 | Complete Environmental Permitting necessary to implement the Mitigation Plan | PCSWM
16 | Begin project implementation | PCSWM
17 | Project achievement of performance measures | PCSWM
18 | Credits Released | IRT